## Sheet1
CSI4142 - Project W23
Phase 2- Physical design and data staging
Teamwork - breakdown of duties
Deliverable checklist | Responsible | Expected completion date | Actual completion date | Estimated | Actual | Notes (if any)
| team member(s) |  |  | time (hours) to complete | time (hours) to complete
Create database instance | Victor | March 25th | March 23rd | 1 | 1
Create Cancellation dimension | Jenson | March 15th | March 11th | 0.5 | 0.5
Create Flight Date dimension | Victor | March 15th | March 11th | 0.5 | 0.5
Create Depature Airport dimension | Lootii | March 15th | March 11th | 0.5 | 0.5
Create Airrival Airport dimension | Lootii | March 15th | March 11th | 0.5 | 0.5
Create Aircraft Dimension | Jenson | March 15th | March 11th | 0.5 | 0.5
Create Airline Dimension | Victor | March 15th | March 11th | 0.5 | 0.5
Create Flight Dimension | Victor | March 15th | March 11th | 0.5 | 0.5
Create Fact Table | Jenson | March 15th | March 11th | 0.5 | 0.5
Data staging: Cancellation dimension | Jenson | March 20th | March 18th | 0.5 | 0.5
Data Staging: Flight Date dimension | Victor | March 20th | March 18th | 0.5 | 0.5
Data Staging: Depature Airport dimension | Lootii | March 20th | March 18th | 0.5 | 0.5
Data Staging: Airrival Airport dimension | Lootii | March 20th | March 18th | 0.5 | 0.5
Data Staging: Aircraft Dimension | Jenson | March 20th | March 18th | 0.5 | 0.5
Data staging: Airline Dimension | Victor | March 20th | March 18th | 0.5 | 0.5
Data Staging Flight Dimension | Victor | March 20th | March 18th | 0.5 | 0.5
Data Staging: Fact Table | Jenson | March 20th | March 18th | 0.5 | 0.5
Surrogate key pipeline | Jenson | March 22nd | March 19th | 2 | 1
Staging of fact table – including FKs and measures | Jenson | March 22nd | March 19th | 2 | 1
Data quality handling and reporting | Lootii | March 22nd | March 19th | 2 | 2